## Stacking Shelter Checklist (hidden)
[5 empty] | CO-LOCATION SITE ACCEPTANCE | [7 empty] | Contractor Logo
[5 empty] | Site ID: |  |  | Submit Date:
[5 empty] | Site Name: |  |  | Project:
APPLICABLE FOR STACKING SHELTER WORK
SITE INFORMATION
Site ID | [5 empty] | :
Site Name | [5 empty] | :
Site Address | [5 empty] | :
Installed By | [5 empty] | :
Material Supplied By | [5 empty] | :
Tower Upgrade Type | [5 empty] | :
Inspection Date | [5 empty] | :
Carrier | [5 empty] | :
RFI Date as per Colo Tracker | [5 empty] | :
INSPECTION CHECK LIST
NO |  | INSPECTION ITEM | [6 empty] | ACCEPTANCE |  |  | CRITERIA |  |  | REMARKS
[9 empty] | YES | NO | N/A
1 |  | FOUNDATION (CIVIL WORKS)
| a | Type of foundation
| b | Dimension
|  | - Base | [9 empty] | Conform
|  | - Column | [9 empty] | Conform
|  | - Depth | [9 empty] | Conform
| c | Concrete
|  | - Concrete Strength Certificate | [9 empty] | Provided / Within the specification
|  | - Concrete Surface | [9 empty] | Good
| d | Anchor
|  | - Diameter | [9 empty] | Conform
|  | - Grouting | [9 empty] | Good / Smooth / Done
|  | - Placement | [9 empty] | Firmly fixed / Conform
|  | - Level | [9 empty] | Good / Level / Conform
| e | Finishing Works
|  | - Soil Compacting | [9 empty] | Done / Neat / Conform
|  | - Site Cleaning | [9 empty] | Clean / Neat
2 |  | STEEL STRUCTURE
| a | Steel material
|  | - Wide Flange (H-Beam and I-Beam) and Angle Steel | [9 empty] | Mill Certificate provided / Within the specification / Complete and Conform to design / Not Bend or Camber / Galvanized
|  | - Bolt, Nut, Plate Washer and Spring Washer | [9 empty] | Tightened within torque spec / Complete / Galvanized / HTB
|  | - Chequered Plate | [9 empty] | Conform / Galvanized
| b | Installation | [9 empty] | Conform / All member properly connected and installed
| c | Galvanizing Test | [9 empty] | Minimum 85µm / Certified
| d | Holes | [9 empty] | New / Conform / Precise / Galvanized
| e | Welding | [9 empty] | Conform / Galvanized / Neat / No porosity
| f | Stairs | [9 empty] | Conform / Galvanized / Neat
| g | Painting | [9 empty] | Conform / Once / Neat
3 |  | CLEANNESS AND TIDINESS
| a | No trash and garbage arround and inside of site
| b | No excess materials left
REVIEWED AND APPROVED BY: | [6 empty] | ACCEPTANCE TEST BY: |  |  |  | ACCEPTANCE TEST BY:
PT. PROTELINDO | [6 empty] | O & M |  |  |  | Contractor Name
Name: | [6 empty] | Name: |  |  |  | Name:
Place and Date: | [6 empty] | Place and Date: |  |  |  | Place and Date:
Version |  | : | 2 | QC PROTELINDO | [8 empty] | Page: | 1 | of | 2
Revision |  | : | 1 | Eng-QC-TU-Site Acceptance-Form-001 |  |  |  | Form Issued Date: |  |  |  | 2008-07-31

## QC Point and Checklist (hidden)
QC Point and Checklist
No | Inspection Point | No | Item Description | Value | Inspection result | Point | Total Point | Point in words
1 | Material Supply | a | Profile material | 50 | 1 | 50 | 100 | ACC
|  | b | Specification of material | 50 | 1 | 50
2 | Fabrication performance | a | Cutting | 25 | 1 | 25 | 100 | ACC
|  | b | Holing / Punching / Drilling | 25 | 1 | 25
|  | c | Bending | 25 | 1 | 25
|  | d | Welding | 25 | 1 | 25
3 | Installation performance | a | Completeness of material | 14.2857 | 1 | 14.2857 | 100 | ACC
|  | b | Proper connection | 14.2857 | 1 | 14.2857
|  | c | Torque of bolt / bolt tightness | 14.2857 | 1 | 14.2857
|  | d | Welding on site | 14.2857 | 1 | 14.2857
|  | e | Grouting | 14.2857 | 1 | 14.2857
|  | f | Measurement of installed material | 14.2857 | 1 | 14.2857
|  | g | Conformance to design | 14.2857 | 1 | 14.2857
4 | Galvanizing | a | Thickness of galvanizing | 33.3333 | 1 | 33.3333 | 100 | ACC
|  | b | Visual test | 33.3333 | 1 | 33.3333
|  | c | Corrosion | 33.3333 | 1 | 33.3333
5 | Finishing works | a | OBL recondition | 20 | 1 | 20 | 100 | ACC
|  | b | Splitzen recondition | 20 | 1 | 20
|  | c | Waterprofing paint | 20 | 1 | 20
|  | d | Painting | 20 | 1 | 20
|  | e | Cleaness and tidiness of site | 20 | 1 | 20
CONCLUSION | [6 empty] | 500 | Accepted
|  |  | Conclusion |  | Range
|  |  | Accepted |  | > 333.35
|  |  | Accepted With Rectification |  | 166.68 < x < 333.34
|  |  | Rejected |  | < 166.67
|  |  | Inspection result |  | Value
|  |  | Good |  | 1
|  |  | Minor |  | 0.5
|  |  | Major |  | 0

## MASTER
MASTER
Project ID | :
Site Name PO | :
Site Name Tenant | :
Site ID | :
START | : |  | Tanggal :
DONE | : |  | Tanggal :
Tenant | :
Type Tower/Heigh | :
Alamat | :
Koordinat | : | Long :
Lat :
Pekerjaan | :
Area | :
Mitra | : | PT. TRITECH CONSULT INDONESIA
ATP Date | :
PT. TRITECH CONSULT INDONESIA
Executive General Manager | :
Manager Construction | :
PT. Dayamitra Telekomunikasi Tbk
GM Area Office Jabodetabeb & Jabar | :
Manager Const Depl TG & OM Area Office Jabodetabeb Inner | :
Project Management | :
Waspang Area | :

## CHECKLIS MK B2S
rev. 03
CHECKLIS BINDER MK B2S
Project ID |  | : | 0
Site Name |  | : | 0
Site ID |  | : | 0
ATP Date |  | : | 0
NO |  |  | DESCRIPTION | Doc. Type | CHECK |  | REMARK
[5 empty] | Complete | Not Required
1 |  |  | PLANED DOCUMENT
| 1 |  | Offering / penunjukan Mitra dari procurement | Copy
| 2 |  | Purchase Order | Copy
| 3 |  | Undangan Site Opening + BA Site Opening + Foto Mos | Copy
| 4 |  | Undangan pengecoran + BA Pengecoran + Foto Pengecoran | Copy
| 5 |  | RFI Notification + Foto | Copy
| 6 |  | Function Test / Foto ATP & Verticality | Copy
| 7 |  | Acceprence Test Dokumen + Closing Pending | Copy
2 | 8 |  | SS Oneflux | Copy
Submitted by : |  |  |  |  | Checked by :
PT. TRITECH CONSULT INDONESIA |  |  |  |  | MITRATEL RO JABODETABEK
Tanggal: |  |  |  |  | Tanggal:

## EVIDEN
EVIDEN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | TSEL
EVIDEN

## EVIDEN 1
EVIDEN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | TSEL
EVIDEN

## EVIDEN 2
EVIDEN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | TSEL
EVIDEN

## EVIDEN 3
EVIDEN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | TSEL
EVIDEN

## EVIDEN 4
EVIDEN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | TSEL
EVIDEN

## EVIDEN 5
EVIDEN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | TSEL
EVIDEN

## SKOM
SKOM
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | 0
MK ON SITE |  |  | SKOM
SKOM |  |  | SKOM

## PEMBESIAN SITE
DOKUMENTASI PEMBESIAN SITE
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | 0
PEMBESIAN SITE |  |  | PEMBESIAN SITE
PEMBESIAN SITE |  |  | PEMBESIAN SITE
PEMBESIAN SITE |  |  | PEMBESIAN SITE

## PENGECORAN SITE
DOKUMENTASI PENGECORAN
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | 0
MK ON SITE |  |  | PERSIAPAN PENGECORAN
PENGECORAN |  |  | PENGECORAN
PENGECORAN |  |  | PENGECORAN
PENGECORAN |  |  | PENGECORAN

## MOS & ERECTION
MOS & ERECTION
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | 0
MK ON SITE |  |  | MATERIAL ON SITE
MATERIAL ON SITE |  |  | ERECTION
ERECTION |  |  | ERECTION

## PELAKSANAAN ATP
DOKUMENTASI ATP/FUNCTION TEST
SITE ID | : | 0
SITE NAME | : | 0
TENANT | : | 0
FOTO MK |  |  | SITE VIEW
`
PANEL ACPDB |  |  | PANEL KWH
`
GROUNDING |  |  | GROUNDING
PENGUKURAN TEGANGAN RS |  |  | PENGUKURAN TEGANGAN RN
PENGUKURAN TEGANGAN RT |  |  | PENGUKURAN TEGANGAN SN
PENGUKURAN TEGANGAN ST |  |  | PENGUKURAN TEGANGAN TN
PENGUKURAN TEGANGAN NG |  |  | PENGUKURAN TEGANGAN
PENGUKURAN TEGANGAN |  |  | PENGUKURAN TEGANGAN
PENGUKURAN TEGANGAN |  |  | PENGUKURAN TEGANGAN
PENGUKURAN TEGANGAN |  |  | PENGUKURAN TEGANGAN
VERTICALITY |  |  | VERTICALITY
VERTICALITY |  |  | VERTICALITY